## Ark1
Risk managment Matrix |  |  |  | Rating
Category | Risk | What | Origin | Strategy of acting | Likelihood | Severity | Detectability | Sum of rating
Environment | R1 | Customer dissatisfied with process or project outcome | KTP, HSN | Protect | Low | High | Medium | HML
SAFETY | S1 | LIPO taking fire |  | Charge batty in fire safe bag. Only charge when people are under supervision. Charge battery after manufacturers instructions. Never drop the battery on the ground. | Low | Low | Low | LLL
SAFETY | S2 | Quadcopter propeller cut human |  | Only fly quad inside the web at KIC. Redudant deadswitch. Propeller blocker. | Low | Low | Low | LLL
SAFETY | S3 | Getting shocked from the power system on the quad. |  | Always ensure that all wires has insulation. Ensure that all connectors is propper heatshrinked. | Low | Low | Medium | MLL
SAFETY | S4 | Getting injured while working on machinery. |  | Always ensure that proper coursing on given machinery has been performed. Always ensure that there are always two people working on machinery. | Low | Low | Low | LLL
LABOR | L1 | Long time sick leave |  | Nothing to do about, but we are young and fresh, so the probability of long time sickness low. More than two gone for a long time would put the project deadline at huge risk. | low | High | Low | HLL
LABOR | L2 | Low competance in technical fields |  | Low competance in technical fields could put the project deadline at risk. Since the project deadline is fixed and cannot be moved, slow progression is a major risk. But the group consists of highly motivated, technical experienced members who tend to solve most problems. | Medium | High | Low | HML
|  | Ordering wrong parts |  | Ordering wrong parts is setting the project at low risk if ordered in the early project stage. If the order is close to the deadline, it can put the project at severe risk. Its important to always double check the order. | Medium | Medium | Low
|  | Delayed delivery of parts |  | Delayed delivery of parts has the same risk as above. | Medium | Medium | Low
|  | Out of spare parts |  | Getting out of spare parts has an low risk, because we have access to two labs with equipment and parts. We also have contacts who has access to quadcopter parts, which we can borrow. | Low | Low | High
|  | Not enough time to make project deadline |  | Breaking up the project into several major milestones. With different difficulty makes it sure that we will make the project deadline. | Low | High | Medium
Low quality requirements, wrong stated requirements, not defined requirements, not fulfilled requirements.
Technical problems
Bad communication/wrongful communication
Not having tools or equipment.